## project
Development Project Planner
WEEK NUMBER AND WEEK BEGINNINGS
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TASK | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2016-01-02 | 2016-01-09 | 2016-01-16 | 2016-01-23 | 2016-01-30 | 2016-02-06 | 2016-02-13 | 2016-02-20 | 2016-02-27 | 2016-03-06 | 2016-03-13 | 2016-03-20 | 2016-03-27 | 2016-04-03 | 2016-04-10 | 2016-04-17 | 2016-04-24 | 2016-05-01
Tile-Based Game Development Research and Backbone Coding | 2016-10-31 | 2 | 2016-10-31 | 2 | WEEK NUMBER AND WEEK BEGINNINGS 8: Christmas
Character Development Research | 2016-11-14 | 1 | 2016-11-14 | 1 | bar: WEEK NUMBER AND WEEK BEGINNINGS 3
Character Coding | 2016-11-21 | 1 | 2016-11-21 | 1
AI Pathfinding Research | 2016-11-28 | 1 | 2016-11-28 | 1 | bar: WEEK NUMBER AND WEEK BEGINNINGS 5
AI Pathfinding Coding and Testing | 2016-12-05 | 2 | 2016-12-05 | -
Character AI Research | 2016-01-02 | 2 | - | - | bar: WEEK NUMBER AND WEEK BEGINNINGS 10 to WEEK NUMBER AND WEEK BEGINNINGS 11
Employee AI Research and Development | 2016-01-16 | 2 | - | -
Employee AI Coding | 2016-01-30 | 2 | - | - | bar: WEEK NUMBER AND WEEK BEGINNINGS 14 to WEEK NUMBER AND WEEK BEGINNINGS 15
Employee AI Testing | 2016-02-13 | 1 | - | -
Customer AI Research and Development | 2016-02-20 | 2 | - | - | bar: WEEK NUMBER AND WEEK BEGINNINGS 17 to WEEK NUMBER AND WEEK BEGINNINGS 18
Customer AI Coding | 2016-03-06 | 2 | - | -
Customer AI Testing | 2016-03-20 | 1 | - | - | bar: WEEK NUMBER AND WEEK BEGINNINGS 21
Other Game-Play Systems Research and Development | 2016-03-27 | 2 | - | -
General Coding Tidy-Up and Alpha Testing | 2016-04-10 | 1 | - | - | bar: WEEK NUMBER AND WEEK BEGINNINGS 24
Beta Testing | 2016-04-17 | 1 | - | -
Final Report Development and Creation | 2016-04-24 | 2 | - | - | bar: WEEK NUMBER AND WEEK BEGINNINGS 26 to WEEK NUMBER AND WEEK BEGINNINGS 27